## Sheet1
po_razin_id | po_created_date | po_approval_date | supplier_confirmation_date | pi_invoice_approval_date | pi_payment_date | receive_first_prd_date | prd_reconfirmed_date | po_im_date_value | po_sm_date_value | batch_created_ts | sm_signoff_ts | ci_invoice_approval_date | ci_payment_date | qc_schedule_date | ffw_booking_ts | spd_ts | stock_pickup_date | shipment_creation_date | shipment_in_transit_date | bi_invoice_approval_date | bi_payment_date | ffwp_telex_release_date | shipment_stock_delivery_date | item_receipt_date | actual_cargo_pick_up_date | actual_shipping_date | actual_arrival_date | actual_delivery_date | first_prd_date | final_prd_date | planned_prd | batch_spd | qi_date | pi_terms | pi_applicable | ci_terms | ci_applicable | plt | 01. PO Approval Pending_Date | 01. PO Approval Pending_Delay_Days | 01. PO Approval Pending_Status | 02. Supplier Confirmation Pending_Date | 02. Supplier Confirmation Pending_Delay_Days | 02. Supplier Confirmation Pending_Status | 03. PI Upload Pending_Date | 03. PI Upload Pending_Delay_Days | 03. PI Upload Pending_Status | 04. PI Approval Pending_Date | 04. PI Approval Pending_Delay_Days | 04. PI Approval Pending_Status | 05. PI Payment Pending_Date | 05. PI Payment Pending_Delay_Days | 05. PI Payment Pending_Status | 06. Packaging Pending_Date | 06. Packaging Pending_Delay_Days | 06. Packaging Pending_Status | 07. Transparency Label Pending_Date | 07. Transparency Label Pending_Delay_Days | 07. Transparency Label Pending_Status | 08. PRD Pending_Date | 08. PRD Pending_Delay_Days | 08. PRD Pending_Status | 09. Under Production_Date | 09. Under Production_Delay_Days | 09. Under Production_Status | 10. PRD Confirmation Pending_Date | 10. PRD Confirmation Pending_Delay_Days | 10. PRD Confirmation Pending_Status | 11. IM Sign-Off Pending_Date | 11. IM Sign-Off Pending_Delay_Days | 11. IM Sign-Off Pending_Status | 12. Ready for Batching Pending_Date | 12. Ready for Batching Pending_Delay_Days | 12. Ready for Batching Pending_Status | 13. Batch Creation Pending_Date | 13. Batch Creation Pending_Delay_Days | 13. Batch Creation Pending_Status | 14. SM Sign-Off Pending_Date | 14. SM Sign-Off Pending_Delay_Days | 14. SM Sign-Off Pending_Status | 15. CI Approval Pending_Date | 15. CI Approval Pending_Delay_Days | 15. CI Approval Pending_Status | 16. CI Payment Pending_Date | 16. CI Payment Pending_Delay_Days | 16. CI Payment Pending_Status | 17. QC Schedule Pending_Date | 17. QC Schedule Pending_Delay_Days | 17. QC Schedule Pending_Status | 18. FFW Booking Missing_Date | 18. FFW Booking Missing_Delay_Days | 18. FFW Booking Missing_Status | 19. Supplier Pickup Date Pending_Date | 19. Supplier Pickup Date Pending_Delay_Days | 19. Supplier Pickup Date Pending_Status | 20. Pre Pickup Check_Date | 20. Pre Pickup Check_Delay_Days | 20. Pre Pickup Check_Status | 21. FOB Pickup Pending_Date | 21. FOB Pickup Pending_Delay_Days | 21. FOB Pickup Pending_Status | 22. Non FOB Pickup Pending_Date | 22. Non FOB Pickup Pending_Delay_Days | 22. Non FOB Pickup Pending_Status | 23. INB Creation Pending_Date | 23. INB Creation Pending_Delay_Days | 23. INB Creation Pending_Status | 24. Mark In-Transit Pending_Date | 24. Mark In-Transit Pending_Delay_Days | 24. Mark In-Transit Pending_Status | 25. BL Approval Pending_Date | 25. BL Approval Pending_Delay_Days | 25. BL Approval Pending_Status | 26. BL Payment Pending - In Transit_Date | 26. BL Payment Pending - In Transit_Delay_Days | 26. BL Payment Pending - In Transit_Status | 27. BL Payment Pending - Arrived_Date | 27. BL Payment Pending - Arrived_Delay_Days | 27. BL Payment Pending - Arrived_Status | 28. Telex Release Pending_Date | 28. Telex Release Pending_Delay_Days | 28. Telex Release Pending_Status | 29. Stock Delivery Pending_Date | 29. Stock Delivery Pending_Delay_Days | 29. Stock Delivery Pending_Status | 30. Stock Receiving Pending_Date | 30. Stock Receiving Pending_Delay_Days | 30. Stock Receiving Pending_Status | 31. Dispute - PO Closing Pending_Date | 31. Dispute - PO Closing Pending_Delay_Days | 31. Dispute - PO Closing Pending_Status
PO373283MOUN-0000071 | 2025-05-12 | 2025-05-13 | 2025-05-21 | 2025-05-26 | 2025-05-29 | 2025-05-23 | 2025-06-13 | 2025-06-16 | 2025-06-17 | 2025-06-17 11:00 | 2025-06-18 09:46 |  |  |  | 2025-06-18 12:38 | 2025-06-20 05:30 |  |  |  | 2025-06-20 | [8 empty] | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-07 |  | 30 | 1 | 0 | 0 |  | 2025-05-13 | 1 | delayed | 2025-05-21 | 5 | delayed | 2025-05-26 | 4 | delayed | 2025-05-26 | -2 | early | 2025-05-29 | -2 | early | 2025-06-01 |  | unknown | 2025-05-31 |  | unknown | 2025-05-31 | -8 | early | 2025-06-07 |  | unknown |  |  | unknown | 2025-06-16 | 0 | on_time | 2025-06-17 | 0 | on_time | 2025-06-17 | -1 | early | 2025-06-18 | -2 | early |  |  | unknown |  |  | unknown | 2025-06-20 | 10 | pending_overdue | 2025-06-21 | -3 | early | 2025-06-24 | -5 | early | 2025-06-25 | 5 | pending_overdue | 2025-06-27 | 3 | pending_overdue | 2025-06-27 | 3 | pending_overdue | 2025-06-28 | 2 | pending_overdue | 2025-07-01 |  | pending | 2025-07-02 | -13 | early | 2025-07-07 |  | pending | 2025-07-05 |  | pending | 2025-07-08 |  | pending | 2025-07-10 |  | pending | 2025-07-11 |  | pending | 2025-07-13 |  | unknown
PO373323PXIN-0001031 | 2025-05-12 | 2025-05-13 | 2025-05-21 |  |  | 2025-05-26 | [22 empty] | 2025-08-11 | 2025-08-11 | 2025-08-11 |  |  | 0 | 0 | 0 | 0 |  | 2025-05-13 | 1 | delayed | 2025-05-21 | 5 | delayed | 2025-05-22 | 39 | pending_overdue | 2025-05-24 | 37 | pending_overdue | 2025-05-29 | 32 | pending_overdue | 2025-05-24 |  | unknown | 2025-05-23 |  | unknown | 2025-05-26 | 3 | delayed | 2025-06-02 |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown
PO373366ROOM-0337551 | 2025-05-12 | 2025-05-13 | 2025-05-26 | 2025-05-27 | 2025-06-02 | 2025-06-04 | [22 empty] | 2025-07-22 | 2025-07-22 | 2025-07-22 |  |  | 50 | 1 | 0 | 0 |  | 2025-05-13 | 1 | delayed | 2025-05-26 | 10 | delayed | 2025-05-27 | 0 | on_time | 2025-05-27 | -2 | early | 2025-06-02 | 1 | delayed | 2025-06-05 |  | unknown | 2025-06-04 |  | unknown | 2025-06-04 | 0 | on_time | 2025-06-11 |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown
PO373771AMAZ-0002481 | 2025-05-12: 2025-05-27; 2025-05-13: 2025-06-04 | [22 empty] | 2024-09-20 | 2024-09-20 |  |  |  | 10 | 1 | 0 | 0 |  | 2025-06-04 | 8 | delayed | 2025-06-07 | 23 | pending_overdue | 2025-06-08 | 22 | pending_overdue | 2025-06-10 | 20 | pending_overdue | 2025-06-15 | 15 | pending_overdue | 2025-06-18 |  | unknown | 2025-06-17 |  | unknown | 2025-06-17 | 13 | pending_overdue | 2025-06-24 |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown
PO373857M2B3-10030650 | 2025-05-12: 2025-05-28; 2025-05-13: 2025-06-04 |  |  |  | 2024-06-28 12:35 | 2025-01-28 06:26 |  |  |  | 2024-11-18 16:06 | 2025-02-26 18:20 | [12 empty] | 2024-04-01 | 2024-06-30 |  | 2025-01-15 |  | 10 | 1 | 0 | 0 |  | 2025-06-04 | 7 | delayed | 2025-06-07 | 23 | pending_overdue | 2025-06-08 | 22 | pending_overdue | 2025-06-10 | 20 | pending_overdue | 2025-06-15 | 15 | pending_overdue | 2025-06-18 |  | unknown | 2025-06-17 |  | unknown | 2025-06-17 | 13 | pending_overdue | 2025-06-24 |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown |  |  | unknown | 2025-01-28 | 213 | delayed |  |  | unknown |  |  | unknown | 2025-01-30 | 151 | pending_overdue | 2025-01-31 | -74 | early | 2025-02-26 | 23 | delayed | 2025-02-27 | 123 | pending_overdue | 2025-03-01 | 121 | pending_overdue | 2025-03-01 | 121 | pending_overdue | 2025-03-02 | 120 | pending_overdue | 2025-03-05 | 117 | pending_overdue | 2025-03-06 | 116 | pending_overdue | 2025-03-11 | 111 | pending_overdue | 2025-03-09 | 113 | pending_overdue | 2025-03-12 | 110 | pending_overdue | 2025-03-14 | 108 | pending_overdue | 2025-03-15 | 107 | pending_overdue | 2025-03-17 |  | unknown